## Slide 1: Involuntary Off-boarding After-Action Review (AAR)
2022-04-08
Remote (Microsoft Teams)
Notes: This template is for After-Action Reviews. Please use this to collect feedback during reviews by typing comments directly into an instance of this template or collect AAR comments in another document for dissemination later.

## Slide 2
After-Action Review Details
Date of AAR: 2022-04-06
Location: remote (MS Teams)
Participants:
Brandon Fogarty
Andrea Brown
Kim Doner
Christopher Burch (facilitator)
Notes: Record relevant details

## Slide 3
Project / Event Details
Date of event: 2022-02-25
Location: [location of event]
Participants: [list participants]
Notes: Record relevant details

## Slide 4
What did we intend to do / what was supposed to happen?
GLT decided to part ways with employee
GLT policy is to not provide notice to offboarded employees
Notes: Ask participants to describe the intent or goal of the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects. Discovering how participants think about the task will she light on the connections between how a task is perceived by different participants and may lead to understanding of root causes of successes or failures.

## Slide 5
What actually occurred?
Managers decided to offboard employee
  Consistent errors, remediation attempted
  Reviewed work product
  No improvement
  Performance had been an issue
  Employee notified on several occasions re performance, written & verbal
Employee response
  No “pushback”, accepted review and criticism
Difficulty finding replacement
  Rep not found until Feb
  Didn’t want to leave position vacant
  Replacement found mid-Feb, started late Feb
GLT expects four weeks notice, does not provide notice to employees
  Executive decision to not provide notice due to risk of reputational harm to firm
Notes: Ask participants to describe what transpired during the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects.

## Slide 6
What actually occurred?
Does not providing notice protect from that risk?
  Employee may feel slighted by non-notice and this may increase the risk of harm
Past split caused issue
Employee response to firing
Unexpected, shocked
Brandon – I would have expected “red flag”
After her review, employee sent response indicating she would improve
Focused on financial implications of firing
Former employee trying to connect with Kim on LinkedIn
She reached out to former team members
Probably not an issue
Found another position
Notes: Ask participants to describe what transpired during the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects.

## Slide 7
What actually occurred?
Employee needed data from iSolved for unemployment but no longer had access
Brandon called Ivan directly, he facilitated
Documentation of warnings
Shared with HR
Ivan asked Brandon to fill out paperwork for VA (state) recording warnings, etc.
Communication over multiple channels
Ivan on vacation
Text messages
Phone calls
Notes: Ask participants to describe what transpired during the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects.

## Slide 8
What went well, and why?
GLT looked for opportunities to place employee in another company role
Empathy
Managers did a good job of communicating
  Emails, teams, phone calls
  Discussed at weekly meeting
HR provides basic nec info already
Notes: What went well?
Why?
If possible, dig deeper to find root causes.
How can we institutionalize or sustain that effort going forward?

## Slide 9
What could be improved, and how?
Notice to offboarding employees?
  Execs: not gonna happen
Severance at date of termination
  Non-egregious act / no malice
Employee needed data from iSolved for unemployment but no longer had access
  Provide required documents (W-2) automatically on termination
  Archive, not delete?
Should managers fill out State forms re firings, etc?  should be HR function
Employee < 3 rating should require a formal performance improvement plan in place with milestones
Notes: What didn’t go well, or could have gone better?
If possible, dig to find root causes of potential improvements. Suggest steps to address these root causes.
Each improvement should include a suggestion for how to mitigate or alleviate the issue in the future. Sometimes simply being aware of an issue is a good first step in remediation.

## Slide 10
What could be improved, and how?
Brandon: HR support
  Kim: HR improvement program in progress (next week)
  Help writing job descriptions (more specific to the role)
  More pre-screening of candidates – writing test?
  Tracking – confusion about position, description, agency, departments, managers, team leaders, etc. Currently comes piecemeal, needs to be in a central location for managers to access
Could GLT connect terminated employees with recruiters? Or a link to job / unemployment resources as part of offboarding?
  Termination vs laid off
More formal processes
With new employees: 30-60-90 reviews
  One-on-one meetings with employees, check-in
  Track professional development plan
HR coverage
Notes: What didn’t go well, or could have gone better?
If possible, dig to find root causes of potential improvements. Suggest steps to address these root causes.
Each improvement should include a suggestion for how to mitigate or alleviate the issue in the future. Sometimes simply being aware of an issue is a good first step in remediation.

## Slide 11
Activities / actions to sustain
Empathy
  From a company perspective
  Open communication
  Try to place elsewhere to new positions in company
Notes: Collect a listing of:
Items to sustain – things that went well and should be encouraged going forward. Include ideas on how to institutionalize these items if possible.
Items to improve or avoid – specific issues to watch out for next time, and ways to test for, anticipate, and reduce the impact of these negative events
Anything else the group wants to note (praise is OK, blame is not; try to think in terms of the next team to do this)

## Slide 12
Activities / actions to improve or avoid
Need PIP for low performance reviews
Formal review periods for new hires
Documentation
  Provide relevant files from HR system to employee on termination
  Written review plans/performance, bcc to HR
Training for Managers
  Termination procedures
  Counseling
HR coverage

## Slide 13
Questions / Comments
Notes: Any additional comments?
Now is also the time to make sure attendance is accurate – collect emails and send out notes afterwards