## Slide 1: 2021 Annual Personal Property Education Workshop After-Action Review (AAR)
2021/09/27
Facilitator: Christopher Burch
Notes: This template is for After-Action Reviews. Please use this to collect feedback during reviews by typing comments directly into an instance of this template or collect AAR comments in another document for dissemination later.

## Slide 2
Project / Event Details
Date of event: September 21-23, 2021
Location: virtual (Microsoft Teams)
Participants: see APM-400 2021 Personal Property Education Workshop Agenda
Notes: Record relevant details

## Slide 3
AAR Details
Date of AAR: September 27, 2021
Location: virtual (Microsoft Teams)
Participants:
GLT: Marla Williams, Kim Doner, Angela Randolph, Hrishikesh Sanghani, Michael Anduha, Sulvia Doja, Christopher Burch
FAA: Kendal Horton
POC: Christopher Burch (christopher.burch@grantleadingtechnology.com)
Notes: Record relevant details

## Slide 4
Critique
A primarily one-way flow of feedback about an individual or group’s performance
Takes less time to conduct
Useful when the participant’s ability to analyze their own performance is limited
Evaluator
Participant
Participant
Participant
Notes: Intro to AAR process – skip if not needed
A critique is usually a one-way exchange of information

## Slide 5
Debrief
The process of retrieving information from participants
Usually, a one-way upstream flow of information
Structured and quick method of information capture
Evaluator
Participant
Participant
Participant
Notes: Intro to AAR process – skip if not needed
A debrief is also a one-way exchange of information, from the participants to an evaluator / leader

## Slide 6
After-Action Review (AAR)
A process to collect and evaluate lessons learned
Facilitator
Participant
Participant
Participant
Notes: Intro to AAR process – skip if not needed
An AAR is a multi-layer feedback and knowledge discovery process and is significantly distinct in tone and purpose from a critique and debrief. It focuses more on the difference between expectations and reality than blame for outcomes, and seeks to find root causes for issues or successes.

## Slide 7
What is an After-Action Review (AAR)?
A tool to capture lessons learned
A dynamic, professional, and candid discussion of an event
NOT a critique or complaint setting or a full-scale evaluation report
Answers 4 major questions:
  1. What was supposed to happen?
  2. What actually occurred?
  3. What went well, and why?
  4. What can be improved, and how?

## Slide 8
What did we intend to do / what was supposed to happen?
Training workshop to APM
Learning experience for APM-4XX
Speakers/sessions for all disciplines
Informational
For all APM-4XX personnel
And property officers outside APM-4XX
Notes: Ask participants to describe the intent or goal of the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects. Discovering how participants think about the task will she light on the connections between how a task is perceived by diffetent participants and may lead to understanding of root causes of successes or failures.

## Slide 9
What actually occurred?
Rec task from Kendal – annual req.
Planning – meetings to discuss topics – Marla, Kendal, Kim, Tim
several meetings cancelled, supposed to be weekly
ID potential speakers – ID by discipline, subject
AJ Sharma -> req for speaker from his group
Eugene -> same (Marla asked for elec. Fleet)
Marla created proposed list
Tim proposed list -> OMBA119, disp. Methods
Kim – PPMS
Kendal
good communication though process
Notes: Ask participants to describe what transpired during the activity from their point of view and in their own words.
Sometimes different participants will have different views of the task and will emphasize different aspects.

## Slide 10
Actual
Schedule dates – Kendal 2 date ranges, sent to Dan (APM410), Dan selected appropriate date range, Kendal used that to schedule, sent out save the date email
Kendal is organizer; would have been pref. for GLT to take admin role but Teams limitations prevented
breakout sessions pre-scheduled – potential issues with unexpected adds
Develop proposed agenda – started with 2 days but needed more time, pushed to 3 days
Kendal pulled agenda from last year, adjusted as necessary
Labor relations shares with Union, union needs notification, all changes need to be pushed to LR, Tim sends agendas and topics to LR

## Slide 11
Actual
Marla provided templates for presentations
Decisions about breakout rooms changed at last minute
Breakouts went smoothly, Kendal made sure ppl were in correct rooms (support, Tim, Dan, managers), Kendal moved between rooms.
Marla: group didn’t get to all assigned subjects due to unexpectedly long discussions, military crypto discussion, criteria for assigning property to classes, valid discussions
Kendal briefed on purpose of breakouts but maybe not all understood
Kim used spreadsheet instead of PPT – last minute decision. Anticipated audience reaction and adjusted, worked well
Difficulty with assigning latecomers to a room

## Slide 12
Actual
Angie tasked with recording questions and answers
Marla tasked via email.
Difficult to record, felt criticized for not capturing all information, Angie asked to record session, but could not. Misses conversations, rapid fire questions difficult to record.
Speakers who had subject matter expertise were presenting and could not record
Last year Hrishikesh took attendance 3 times per day and recorded present for each session, allowed for partial credit when needed. Only one attendance taken this time per day. Kendal could DL attendance list per session. Requirement for multiple collections not explicit. Technical issues prevented breakout room records

## Slide 13
Kim – Tim suggested topics, coordinated with other parties (Mike, GSA) GSA provided slides, Kim added more info. Had to do research on OMB119. Kim did rehearsals to collect timing. Shared slides with Marla and Marla provided feedback
Kendal: it was good when Marla scheduled rehearsals – multiple sessions allowed for speakers to choose which section to attend
Sulvia – topic suggested by Tim, coordinated with Eugene to deconflict. Overhaul of prev. pres. Marla provided feedback. Rehearsed on own to collect timing
Marla: Tim suggested part of presentation (ECC) and VCS. Used onld presentation as base, created breakout sessions, decided to add automation portion. Feels like she’s told to get out of details and go high-level, but she thinks managers need more details.
Asked for input from manages but got very little input for topics.

## Slide 14
Kendal will send out survey (eLMS), will not make it required
Attendees will get elms credit (internal trng)
Will post Q&A and training slides
Marla did the training slides at conclusion of each day (except Thursday)
Hrishikesh kept timing, breaks

## Slide 15
What went well, and why?
Relevant topics
Audience participation – good Q’s asked; “overlook the obvious” which come back as questions; questions anticipated next topic; helpful for presenters
Kim’s presentation went well
Mike – paid attention, made Kim look good
Sulvia: team participation, not just audience
Notes: What went well?
Why?
If possible, dig deeper to find root causes.
How can we institutionalize or sustain that effort going forward?

## Slide 16
What could be improved, and how?
Timing for presentations  ask for presentations in advance (don’t always get), rehearsals good but not always an option
Sizing / font size  use templates
Manager talking negatively about new process, causing an issue with other PAX in the meeting (Marla anticipated this)  bring up issue with Tim; policy?; Marla: not out role to address this; Kim: management needs to visibly support new policy/processes; Marla: provide presentations ahead of time for comment; Kendal: links provided and not used previously; init instructions were to only discussion national policy, asked to include additional detail but later criticized for including that level of detail
Notes: What didn’t go well, or could have gone better?
If possible, dig to find root causes of potential improvements. Suggest steps to address these root causes.
Each improvement should include a suggestion for how to mitigate or alleviate the issue in the future. Sometimes simply being aware of an issue is a good first step in remediation.

## Slide 17
Instructions to our staff and participants are made clear up front; conflicting instructions on when to read out comments and questions  guidance for presentations and attendees
eg put questions in chat or hold questions to the end
SOP hold questions until end
let comments exist in chat but don’t nec read aloud during the presentation
Asked managers for input on presentations ahead of time, but got very little response back  have Tim reach out and ask for input on topics; more likely to get input from property officers than from property managers

## Slide 18
Conclusions / Recommendations
Activities / actions to sustain
Breaks  make shorter (50:10)
Teamwork  keep being awesome
Activities / actions to improve or avoid
Attendance  every session
Notes: Collect a listing of:
Items to sustain – things that went well and should be encouraged going forward. Include ideas on how to institutionalize these items if possible.
Items to improve or avoid – specific issues to watch out for next time, and ways to test for, anticipate, and reduce the impact of these negative events
Anything else the group wants to note (praise is OK, blame is not; try to think in terms of the next team to do this)

## Slide 19
Questions / Comments
Voluntary consensus standards comparisons
FSC class
ECC class
Notes: Any additional comments?
Now is also the time to make sure attendance is accurate – collect emails and send out notes afterwards